## Debian
Debian Bug #	Status Debian	DCMTK Issue #	DCMTK Issue Status	DCMTK TODO
#675448	Outstanding bugs -- Important bugs; Confirmed	#307	Closed	Nothing
#697073	Outstanding bugs -- Important bugs; Confirmed	None	(no issue)	Check bug with file linked at debian (retry if SF is down)
#748403	Outstanding bugs -- Normal bugs; Unclassified	#815	New	Fix bug
#913227	Outstanding bugs -- Normal bugs; Unclassified	None	(no issue)	Nothing, fixed in https://git.dcmtk.org/?p=dcmtk.git;a=commit;h=dba269a958d9ca44d5af8570e125831d25f63cb3
#913585	Outstanding bugs -- Normal bugs; Unclassified	None	(no issue)	Check bug?
#731433	Outstanding bugs -- Normal bugs; Will Not Fix	#759	Closed	Nothing
#810926	Outstanding bugs -- Normal bugs; Will Not Fix	None	(no issue)	Nothing, already fixed by removing related file
#900196	Outstanding bugs -- Minor bugs; Patch Available	None	(no issue)	Nothing, fixed in http://git.dcmtk.org/?p=dcmtk.git;a=commit;h=3522835b65b4887dc4cbf794abf7e66e9db5079e
#730610	Outstanding bugs -- Wishlist items; Confirmed	#583	New	Fix bug
#637687	Outstanding bugs -- Wishlist items; Will Not Fix	None	(no issue)	Check bug?
#714943	Outstanding bugs -- Wishlist items; Will Not Fix	None	(no issue)	Check bug?
#715029	Outstanding bugs -- Wishlist items; Will Not Fix	None	(no issue)	Nothing, fixed in http://git.dcmtk.org/?p=dcmtk.git;a=commit;h=7a000a8bc84d58fab5368964d49757f7e33036b2
#718557	Outstanding bugs -- Wishlist items; Will Not Fix	None	(no issue)	Check bug?
#859202	Forwarded bugs -- Normal bugs	#600	Closed	Nothing, fixed in http://git.dcmtk.org/?p=dcmtk.git;a=commit;h=35bc7e6fd60d8eca70e04fb0b32b8303806bc494
#935879	Forwarded bugs -- Normal bugs	#344	New	Implement feature
#724886	Forwarded bugs -- Wishlist items	#552	New	Implement feature

Last Check: 2020-08-24

## Ubuntu (TODO)
Ubuntu Bug #	Ubuntu Bug Title	Status Ubuntu	DCMTK Issue #	DCMTK Issue Status	DCMTK TODO
#1487389	SIGSEGV on threaded copy of DcmFileFormat	New – Undecided Importance – Unassigned	None	(no issue)	Check bug?
#1702307	libiconv not found, so character conversion unsupported	Confirmed – Undecided Importance – Unassigned	None	(no issue)	Nothing, this is related to the package configuration

Last Check: 2020-08-24